## Sprint Backlog
Days | TODO | In progress | Reviewing | Done
1 | Find Code Smells / Find Design Patterns / Review Code Smells / Review Design Patterns / Report | Study code | --- | ---
2 | Find Code Smells / Find Design Patterns / Review Code Smells / Review Design Patterns / Report | Study code | --- | ---
3 | Find Code Smells / Find Design Patterns / Review Code Smells / Review Design Patterns / Report | Study code | --- | ---
4 | Review Code Smells / Review Design Patterns / Report | Find Code Smells / Find Design Patterns | Study code | ---
5 | Review Code Smells / Review Design Patterns / Report | Find Code Smells / Find Design Patterns | --- | Study code
6 | Review Code Smells / Review Design Patterns / Report | Find Code Smells / Find Design Patterns | --- | Study code
7 | Review Code Smells / Review Design Patterns / Report | Find Code Smells / Find Design Patterns | --- | Study code
8 | Review Code Smells / Review Design Patterns / Report | Find Code Smells / Find Design Patterns | --- | Study code
9 | Report | Review Code Smells / Review Design Patterns | Find Code Smells / Find Design Patterns | Study code
10 | Report | Review Code Smells / Review Design Patterns | Find Code Smells / Find Design Patterns | Study code
11 | Report | Review Code Smells / Review Design Patterns | --- | Study code / Find Code Smells / Find Design Patterns
12 | --- | Report | Review Code Smells / Review Design Patterns | Study code / Find Code Smells / Find Design Patterns
13 | --- | Report | --- | Study code / Find Code Smells / Find Design Patterns / Review Code Smells / Review Design Patterns
14 | --- | Report | Report | Study code / Find Code Smells / Find Design Patterns / Review Code Smells / Review Design Patterns
15 | --- | --- |  | Study code / Find Code Smells / Find Design Patterns / Review Code Smells / Review Design Patterns / Report